## Detailed Gantt Chart
Project or Deliverable? | Goal | Task | Date | Duration | End Date | Owner
Deliverable |  | Deliverable 0 | 2017-10-01 | 0 | 2017-10-02 | Team
Project |  | Research | 2017-10-01 | 7 | 2017-10-08 | Team
Project |  | Business Case and Gantt Chart | 2017-10-01 | 7 | 2017-10-08 | Team
Deliverable |  | Deliverable 1 | 2017-10-08 | 0 | 2017-10-08 | Sebastian
Project |  | Architecture Diagram and Project Design | 2017-10-15 | 7 | 2017-10-22 | Team
Deliverable |  | Deliverable 2 | 2017-10-22 | 0 | 2017-10-22 | Michael & Kevin
Project | Set up environment | Set up docker | 2017-11-02 | 4 | 2017-11-06 | Michael
Project | Patient Search Interface | Develop front-end | 2017-11-05 | 7 | 2017-11-12 | Chris
Project | Patient Search Interface | Develop FHIR request to pull patient information | 2017-11-05 | 7 | 2017-11-12 | Chirs
Project | SDH Check | Extract patient zip code from FHIR API call | 2017-11-12 | 7 | 2017-11-19 | Chris
Project | SDH Check | Put together list of zip codes with transportation score | 2017-11-02 | 4 | 2017-11-06 | Sebastian
Project | SDH Check | Identify transportation score threshold | 2017-11-05 | 7 | 2017-11-12 | Sebastian
Deliverable |  | Deliverable 3 | 2017-11-12 | 0 | 2017-11-12 | Myles & Chris
Project | SDH Check | Load zip codes into database | 2017-11-12 | 7 | 2017-11-19 | Myles
Project | SDH Questionaire | Load SDH questionnaire into application | 2017-11-12 | 7 | 2017-11-19 | Chris
Project | Referral Check | Load business logic for referral | 2017-11-19 | 7 | 2017-11-26 | Michael
Project | Referral to transport agency | Return the appropriate referral URL string | 2017-11-26 | 7 | 2017-12-03 | Chris
Deliverable |  | Deliverable 4 | 2017-12-03 | 0 | 2017-12-03 | Sebastian
Deliverable |  | Deliverable 5 | 2017-12-03 | 0 | 2017-12-03 | Team

## Goals
Set up environment
Patient Interface/CDS hook
SDH Check
SDH Questionaire
Referral Check
Referral to transport agency

## High Level Gantt Chart
|  | Task | Date | Duration | End Date
Team Topic Presentation | 2017-10-08 | Application Architectural Design | 2017-10-15 | 7 | 2017-10-22
Project Status Report 1 | 2017-10-15 | Design User Interface | 2017-10-23 | 21 | 2017-11-13
Team Technical Presentation | 2017-10-22 | Backend FHIR interface | 2017-10-23 | 21 | 2017-11-13
Project Status Report 2 | 2017-10-29 | Application Testing | 2017-11-15 | 18 | 2017-12-03
Project Status Report 3 | 2017-11-05
Team Progress Report | 2017-11-12
Project Status Report 4 | 2017-11-19
Project Status Report 5 | 2017-11-26
Team Final Project Presentation | 2017-12-03
Formulas:
End Date = [Date]+21